## Key Dates
Milestone | Date | Notes
Supervisor project list released | 2025-03-18
Levelling up Activity 1 | 2025-03-20 | 12:00
Consultation period starts | 2025-03-18
Consultation period ends | 2025-04-17
Deadline for agreeing project with supervisor | 2025-04-24
Project allocation results released | 2025-05-08
Levelling up Activity 2 | 2025-05-13 | 12:00-13:00
Project start | 2025-06-01
Project outline and plan submission | 2025-06-12 | Deadline
Final project submission | 2025-09-04 | Research paper, report, code, video
Live demos | 2025-09-07 | Week beginning 7 September

## Weekly Timeline
PROJECT PROGRESS DASHBOARD
Total Tasks: | Completed: | Blocked: | Overall Progress: | Next Deadline:
Week | Dates | Deadline | Progress % | Status | Key Tasks
Week 1 | 1-7 Jun | 2025-06-07 | 0% | Not started | Set up GitLab, Python structure, Adult Income dataset, data exploration, preprocessing, MLP baseline, project outline
Week 2 | 8-14 Jun | 2025-06-12 | 0% | Not started | Finalise dataset/model/scope, train/evaluate scripts, project outline and plan submission
Week 3 | 15-21 Jun | 2025-06-21 | 0% | Not started | train_original, train_retrain, forget/retain split, record metrics
Week 4 | 22-28 Jun | 2025-06-28 | 0% | Not started | Retain fine-tuning, compare against retrain, save results table
Week 5 | 29 Jun-5 Jul | 2025-07-05 | 0% | Not started | Gradient ascent unlearning, gradient ascent + retain recovery, initial experiments
Week 6 | 6-12 Jul | 2025-07-12 | 0% | Not started | Similarity metrics: prediction agreement, probability gap, logit gap, KL divergence
Week 7 | 13-19 Jul | 2025-07-19 | 0% | Not started | Simple MIA implementation, confidence/loss-based attack, report AUC
Week 8 | 20-26 Jul | 2025-07-26 | 0% | Not started | Main experiments (1%, 5%, 10% forget fractions), 3 seeds, save master CSV
Week 9 | 27 Jul-2 Aug | 2025-08-02 | 0% | Not started | Generate plots, runtime/utility, similarity/runtime, MIA signal, begin writing
Week 10 | 3-9 Aug | 2025-08-09 | 0% | Not started | Analyse results, identify trade-offs, write discussion draft
Week 11 | 10-16 Aug | 2025-08-16 | 0% | Not started | Draft 6-8 page research paper with full sections
Week 12 | 17-23 Aug | 2025-08-23 | 0% | Not started | Supporting report, clean repository, README and reproducibility
Week 13 | 24-31 Aug | 2025-08-31 | 0% | Not started | Demo video, finalise figures/tables, proofread
Week 14 | 1-4 Sep | 2025-09-04 | 0% | Not started | Final submission checks and submit

## Coding Plan
Task ID | Component | Task | Description | File/Script | Input | Output | Priority | Status | Start Date | Due Date | Notes
C001 | data.py | Load Adult Income dataset | Download and load Adult dataset | data/adult.csv, data.py | Adult dataset URL | Loaded pandas DataFrame | High | Not started |  | 2025-06-07
C002 | data.py | Implement preprocessing | Categorical encoding, scaling, train/test split | data.py | Raw Adult DataFrame | Preprocessed arrays (X, y) | High | Not started | 2025-06-01 | 2025-06-07
C003 | model.py | MLP model definition | Define 2-3 layer MLP with ReLU | model.py | Input/output dims | PyTorch model class | High | Not started | 2025-06-03 | 2025-06-07
C004 | train.py | Implement train_original | Train MLP on full dataset (R+F) | train.py, data.py, model.py | X, y, hyperparams | Trained model, metrics | High | Not started | 2025-06-08 | 2025-06-15
C005 | train.py | Implement train_retrain | Retrain from scratch on R only | train.py, data.py, model.py | X_retain, y_retain | Retrained model | High | Not started | 2025-06-08 | 2025-06-15
C006 | unlearn.py | Retain fine-tuning | Fine-tune original on retain set only | unlearn.py, train.py | Original model, X_retain, y_retain | Fine-tuned model | High | Not started | 2025-06-22 | 2025-06-28
C007 | unlearn.py | Gradient ascent | Gradient ascent on forget set | unlearn.py | Original model, X_forget, y_forget | Unlearned model v1 | High | Not started | 2025-06-29 | 2025-07-05
C008 | unlearn.py | Gradient ascent + recover | GA + retain-set recovery | unlearn.py, train.py | GA model, X_retain, y_retain | Unlearned model v2 | High | Not started | 2025-07-01 | 2025-07-05
C009 | evaluate.py | Accuracy/F1/AUROC | Compute accuracy, balanced accuracy, F1, AUROC | evaluate.py, sklearn | Model, X_test, y_test | Metrics dict | High | Not started | 2025-06-15 | 2025-06-21
C010 | evaluate.py | Similarity metrics | Prediction agreement, prob gap, logit gap, KL div | evaluate.py | Original model, unlearned model, test data | Similarity scores | High | Not started | 2025-07-06 | 2025-07-12
C011 | mia.py | Membership inference attack | Confidence/loss-based MIA | mia.py | Model, train/test splits | AUC, attack accuracy | High | Not started | 2025-07-13 | 2025-07-19
C012 | run_experiment.py | Experiment loop | Loop over seeds, forget fractions, methods | run_experiment.py, all others | Config file | Results CSV | High | Not started | 2025-07-20 | 2025-07-26
C013 | configs/adult.yaml | Config file | Hyperparams, paths, experiment settings | configs/adult.yaml | Hyperparameters | YAML config | Medium | Not started | 2025-06-01 | 2025-06-14
C014 | utils.py | Utility functions | Data loading, saving, plotting helpers | utils.py | Various | Helper functions | Medium | Not started | 2025-06-05 | 2025-06-30
C015 | README | Documentation | Setup, dataset, running experiments, results | README.md | Code, results | README.md | Medium | Not started | 2025-08-17 | 2025-08-23

## Experiment Tracker
Exp ID | Dataset | Forget % | Seed | Method | Accuracy | Bal. Accuracy | F1 | AUROC | Log Loss | Runtime (s) | Speedup vs Retrain | Pred Agree | Prob Gap | Logit Gap | KL Div | MIA AUC | Notes
E001 | Adult | 1% | 1 | Original model
E002 | Adult | 1% | 2 | Original model
E003 | Adult | 1% | 3 | Original model
E004 | Adult | 5% | 1 | Original model
E005 | Adult | 5% | 2 | Original model
E006 | Adult | 5% | 3 | Original model
E007 | Adult | 10% | 1 | Original model
E008 | Adult | 10% | 2 | Original model
E009 | Adult | 10% | 3 | Original model
E010 | Adult | 1% | 1 | Full retrain
E011 | Adult | 1% | 2 | Full retrain
E012 | Adult | 1% | 3 | Full retrain
E013 | Adult | 5% | 1 | Full retrain
E014 | Adult | 5% | 2 | Full retrain
E015 | Adult | 5% | 3 | Full retrain
E016 | Adult | 10% | 1 | Full retrain
E017 | Adult | 10% | 2 | Full retrain
E018 | Adult | 10% | 3 | Full retrain
E019 | Adult | 1% | 1 | Retain fine-tune
E020 | Adult | 1% | 2 | Retain fine-tune
E021 | Adult | 1% | 3 | Retain fine-tune
E022 | Adult | 5% | 1 | Retain fine-tune
E023 | Adult | 5% | 2 | Retain fine-tune
E024 | Adult | 5% | 3 | Retain fine-tune
E025 | Adult | 10% | 1 | Retain fine-tune
E026 | Adult | 10% | 2 | Retain fine-tune
E027 | Adult | 10% | 3 | Retain fine-tune
E028 | Adult | 1% | 1 | Gradient ascent
E029 | Adult | 1% | 2 | Gradient ascent
E030 | Adult | 1% | 3 | Gradient ascent
E031 | Adult | 5% | 1 | Gradient ascent
E032 | Adult | 5% | 2 | Gradient ascent
E033 | Adult | 5% | 3 | Gradient ascent
E034 | Adult | 10% | 1 | Gradient ascent
E035 | Adult | 10% | 2 | Gradient ascent
E036 | Adult | 10% | 3 | Gradient ascent
E037 | Adult | 1% | 1 | Gradient ascent + retain recovery
E038 | Adult | 1% | 2 | Gradient ascent + retain recovery
E039 | Adult | 1% | 3 | Gradient ascent + retain recovery
E040 | Adult | 5% | 1 | Gradient ascent + retain recovery
E041 | Adult | 5% | 2 | Gradient ascent + retain recovery
E042 | Adult | 5% | 3 | Gradient ascent + retain recovery
E043 | Adult | 10% | 1 | Gradient ascent + retain recovery
E044 | Adult | 10% | 2 | Gradient ascent + retain recovery
E045 | Adult | 10% | 3 | Gradient ascent + retain recovery

## Literature Tracker
Paper | Year | Category | Read Status | Notes Complete | Key Contribution | Method | Exact/Approx | Model Type | Eval Metrics | Relevance to Project | Citation Added
Cao & Yang - Machine Unlearning | 2015 | Foundational | Not started | No | [6 empty] | No
Ginart et al. - Making Machine Forgetting Practical | 2019 | Approximate Unlearning | Not started | No | [6 empty] | No
Golatkar et al. - Eternal Sunshine of the Spotless Net | 2020 | Approximate Unlearning | Not started | No | [6 empty] | No
Eldan & Russinovich - Who's Harry Potter? | 2023 | Unlearning Attacks | Not started | No | [6 empty] | No
Shokri et al. - Membership Inference Attacks | 2017 | Privacy Attacks | Not started | No | [6 empty] | No
Carlini et al. - Extracting Training Data from LLMs | 2022 | Privacy Attacks | Not started | No | [6 empty] | No
Deep Unlearn - Benchmarking Framework | 2024 | Benchmarking | Not started | No | [6 empty] | No

## Dissertation Progress
Section | Handbook Requirement | Target Length | Status | Progress % | Evidence Needed | Figures/Tables | Notes
Abstract | Required | 150-250 words | Not started | 0%
Introduction | Required | 800-1200 words | Not started | 0% | Project motivation, scope | 1-2
Literature Review | Required | 2000-3000 words | Not started | 0% | 7+ papers reviewed | 1 table
Methods | Required | 1500-2000 words | Not started | 0% | Dataset, models, metrics | 2-3
Experimentation and Results | Required | 2000-2500 words | Not started | 0% | Experiment results | 4-6
Discussion | Required | 1500-2000 words | Not started | 0% | Trade-offs, limitations | 2
Conclusion and Future Work | Required | 500-800 words | Not started | 0%
Ethics | Required | 300-500 words | Not started | 0% | Data privacy, responsible AI
References | Required | 50+ citations | Not started | 0% | IEEE format
Supporting Report | Required | 2000-3000 words | Not started | 0% | Code documentation | 1
Demo Video | Required | <10 mins | Not started | 0% | Live demonstration |  | MP4 format
GitLab Repository | Required | Clean, reproducible | Not started | 0% | README, requirements.txt

## Supervisor Meeting Log
Meeting Date | Meeting # | Topics Discussed | Decisions Made | Actions for Student | Actions for Supervisor | Deadline | Status | Minutes Sent <48h

## Risk Register
Risk ID | Risk | Probability | Impact | Score | Mitigation | Trigger | Owner | Status
R001 | Gradient ascent damages model utility significantly | Medium | High |  |  |  | Student | Active
R002 | MIA results are weak or ambiguous | Medium | High |  |  |  | Student | Active
R003 | Adult Income dataset too easy/ceiling effect | Low | High |  |  |  | Student | Active
R004 | Implementation takes longer than planned | High | Medium |  |  |  | Student | Active
R005 | Results inconclusive or trade-offs unclear | Medium | High |  |  |  | Student | Active
R006 | Demo/video not ready in time | Low | High |  |  |  | Student | Active
R007 | Scope creep into legal compliance issues | Low | Medium |  |  |  | Supervisor | Active

## Submission Checklist
Item | Required | Due Date | Status | Location | Notes
Research paper PDF | Yes | 2025-09-04 | Not started
Supporting report | Yes | 2025-09-04 | Not started
GitLab repository | Yes | 2025-09-04 | Not started |  | Public/shared with assessors
README.md | Yes | 2025-09-04 | Not started |  | Setup, running, results
requirements.txt | Yes | 2025-09-04 | Not started |  | All dependencies
results/adult_summary.csv | Yes | 2025-09-04 | Not started |  | Master results table
Experiment results CSVs | Yes | 2025-09-04 | Not started |  | By method/setting
Figures and tables | Yes | 2025-09-04 | Not started |  | High-res for report
Demo video (MP4) | Yes | 2025-09-04 | Not started |  | <10 mins, with narration
Declaration/cover sheet | Yes | 2025-09-04 | Not started |  | Sign and submit
IEEE references checked | Yes | 2025-09-04 | Not started |  | Consistent formatting
Supervisor GitLab access confirmed | Yes | 2025-09-04 | Not started
Assessor GitLab access confirmed | Yes | 2025-09-04 | Not started