# ECS8056 MSc AI Themed Research Project Weekly Meeting

## Meeting Minutes

Date and Time: 3/6/2026, Week 1

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 10/6/2026, PGT Lab, 1pm |

Issues discussed:

Initial project planning. Discussed potential datasets, suitable machine learning models and possible evaluation metrics for the machine unlearning project. Discussed the project proposal, due 12 June.

Any issues for the attention of project coordinator:

None.

Action Items:

Create project proposal for 12 June.

Review potential datasets and decide on the most appropriate dataset and overall project approach.

Date and Time: 10/6/2026, Week 2

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 17/6/2026, PGT Lab, 1pm |

Issues discussed:

Discussed progress with the literature review and relevant machine-unlearning papers. Reviewed possible datasets and considered which would be suitable for the project. Discussed using realistic data-deletion and right-to-erasure requests, motivated by GDPR principles, to define the records selected for unlearning.

Any issues for the attention of project coordinator:

None.

Action Items:

Finalise and submit the project proposal by 12 June. Continue reviewing the machine unlearning literature and finalise the initial dataset and deletion approach.

_____________________________________________________________________________________

Date and Time: 17/6/2026, Week 3

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 24/6/2026, PGT Lab, 1pm |

Issues discussed:

Began training the initial model. Discussed the planned machine unlearning approach and how GDPR-related deletion requests could be represented through different subsets of the training data. Decided to evaluate multiple deletion subsets rather than relying on a single deletion experiment.

Any issues for the attention of project coordinator:

None.

Action Items:

Complete the baseline model. Implement an initial unlearning method and test the approach across five deletion subsets.

_____________________________________________________________________________________

Date and Time: 24/6/2026, Week 4

| Present: | No meeting held |
| --- | --- |
| Next meeting: | 1/7/2026, PGT Lab, 1pm |

Issues discussed:

Meeting was not held due to a guest lecture.

Any issues for the attention of project coordinator:

None.

Action Items:

Continue implementing and testing the unlearning methods using the Adult dataset.

_____________________________________________________________________________________

Date and Time: 1/7/2026, Week 5

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 8/7/2026, PGT Lab, 1pm |

Issues discussed:

Continued work on the Adult Income dataset and the machine-unlearning pipeline. Discussed keeping the experimental setup consistent so that the different unlearning methods could be compared fairly.

Any issues for the attention of project coordinator:

None.

Action Items:

Continue the Adult Income experiments and implementation of the unlearning methods. Keep the evaluation and results consistent across methods.

_____________________________________________________________________________________

Date and Time: 8/7/2026, Week 6

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 15/7/2026, PGT Lab, 1pm |

Issues discussed:

Continued the Adult Income experiments and discussed how the approximate unlearning methods should be evaluated. Full retraining would be used as the main reference for comparison.

Any issues for the attention of project coordinator:

None.

Action Items:

Continue the Adult Income experiments. Use full retraining as the reference and continue refining the evaluation metrics.

_____________________________________________________________________________________

Date and Time: 15/7/2026, Week 7

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 22/7/2026, PGT Lab |

Issues discussed:

Continued reviewing the Adult Income experiments. Discussed making the deletion scenarios more realistic rather than relying only on simple percentage-based deletion.

Any issues for the attention of project coordinator:

None.

Action Items:

Continue the Adult Income work and investigate more realistic deletion scenarios.

_____________________________________________________________________________________

Date and Time: 22/7/2026, Week 8

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 29/7/2026, PGT Lab |

Issues discussed:

Reviewed the experimental design and discussed adding a synthetic dataset to provide more control over the data and the deletion scenarios.

Any issues for the attention of project coordinator:

None.

Action Items:

Continue the Adult Income experiments and explore a suitable synthetic dataset with realistic deletion scenarios.

_____________________________________________________________________________________

Date and Time: 29/7/2026, Week 9

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 5/8/2026, PGT Lab |

Issues discussed:

Continued the Adult Income work while exploring synthetic data for more controlled deletion scenarios. CastMe was explored as an additional synthetic example.

Any issues for the attention of project coordinator:

None.

Action Items:

Continue the Adult Income experiments and use the synthetic dataset work to explore more realistic forget sets.

_____________________________________________________________________________________

Date and Time: 5/8/2026, Week 10

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 12/8/2026, PGT Lab |

Issues discussed:

Discussed developing a synthetic kidney-transplant dataset as the main controlled experimental dataset, building on the earlier exploratory work using Adult Income and CastMe. The aim was to support a realistic classification task and several different types of deletion request.

Any issues for the attention of project coordinator:

None.

Action Items:

Finalise and validate the kidney-transplant dataset, define the deletion scenarios, and begin applying the existing machine-unlearning approach.

_____________________________________________________________________________________

Date and Time: 12/8/2026, Week 11

| Present: | Niamh Hughes, Awais Rauf (Microsoft Teams) |
| --- | --- |
| Next meeting: | 19/8/2026, PGT Lab |

Issues discussed:

No in-person meeting was held this week; project discussion continued with Awais via Microsoft Teams. The primary use of the hosted Qwen API for data synthesis was clarified, and the data-synthesis approach described in Section 2 of TOFU was reviewed.

Any issues for the attention of project coordinator:

None.

Action Items:

Continue the Qwen-based data-generation and validation work. Review Section 2 of TOFU and the supervisor-provided USAGE.md guidance.

_____________________________________________________________________________________

Date and Time: 19/8/2026, Week 12

| Present: | Niamh Hughes, Awais Rauf |
| --- | --- |
| Next meeting: | 26/8/2026, PGT Lab |

Issues discussed:

Reviewed the SISA results and discussed why the deletion scenarios affected all shards, limiting SISA's efficiency benefit. Discussed the assumptions behind the policy-aware SISA experiment and reviewed the original SISA paper by Bourtoule et al. The methods used in TOFU were also reviewed, and it was agreed that Gradient Difference would be added as a main approximate method while both SISA experiments would be retained as supporting analyses. Awais emphasised that implementations should be checked against published methods or reliable existing code. Further guidance was to use TOFU as inspiration for the final report's structure, figures and tables without copying its wording, and to review MUSE and Right to be Forgotten in the Era of Large Language Models.

Any issues for the attention of project coordinator:

None.

Action Items:

Implement and verify Gradient Difference against the published method. Preserve both SISA experiments and clearly distinguish the standard experiment from the policy-aware exploratory experiment. Read and summarise TOFU, MUSE and the Right to Be Forgotten paper, then use them to plan the final report. Continue consolidating the final results and begin the write-up.

_____________________________________________________________________________________

Date and Time: 26/8/2026, Week 13

| Present: | To be completed |
| --- | --- |
| Next meeting: | 2/9/2026, PGT Lab |

Issues discussed:

Any issues for the attention of project coordinator:

Action Items:

_____________________________________________________________________________________

Date and Time: 2/9/2026, Week 14

| Present: | To be completed |
| --- | --- |
| Next meeting: | Date/Time for the next meeting, online via Microsoft Teams or in person |

Issues discussed:

Any issues for the attention of project coordinator:

Action Items: